## Sheet1
POAP-POS INTEGRATION
PROJECT START DATE |  |  | 13-02-2024 |  | DURATION |  | 1 MONTH
STAKE HOLDER |  |  | Mr.ASHOK/MANJUNTH IYER |  | ARCHITECT |  | VARIJA PAKNIKAR
PROJECT TITLE |  |  | POS INTEGRATION |  | PROJECT STATUS |  | IN PROGRESS
TEAM MEMBER-1 |  |  | VARIJA PAKNIKAR |  | TEAM MEMBER-2 |  | MANJUNATH IYER
SL.NO |  | PROJECT PHASE | TASK | ASSIGNED TO | PLANNED DATE |  | DURUATION (IN DAYS) | ACTUAL DATE |  | STATUS | REMARKS
[5 empty] | START DATE | END DATE |  | START DATE | END DATE
1 | 1.1 | PROJECT PLANNING & INITIATION | PROJECT INITIATION & MAPPING | VARIJA | 13-02-24 | 13-02-24 | 1 DAy | 13-02-24 | 13-02-24 | Completed | Completed | Completed
| 1.3 |  | AS-IS | VARIJA | 14-02-24 | 14-02-24 | 1 Day | 14-02-24 | 14-02-24 | Completed | Completed | In-Progress
| 1.4 |  | TO-BE | VARIJA | 14-02-24 | 14-02-24 | 1 Day | 14-02-24 | 14-02-24 | Completed | Completed | Delay
| 1.5 |  | GAP ANALYSIS | VARIJA | 14-02-24 | 14-02-24 | 1 Day | 14-02-24 | 14-02-24 | Completed | Completed | Hold
| 1.6 |  | WORK AROUND | VARIJA | 15-02-24 | 2024-05-03 | 20 Days | 15-02-24 | 2024-07-03 | In-Progress | Delay, requirement changed
| 1.8 |  | REVIEW & APPROVE | MANJUNATH IYER | 2024-06-03 | 2024-06-03 | 1 Day | 2024-08-03 | 2024-08-03 | Completed | Planned
| 1.9 |  | SIGN OFF SUBMISSION | VARIJA | 2024-07-03 | 2024-07-03 | 1 Day | 2024-09-03 | 2024-09-03 | In-Progress | Planned
| 2 |  | PROJECT APPROVAL SUBMISSION | MANJUNATH IYER | 2024-07-03 | 2024-07-03 | 1 Day | 2024-11-03 | 2024-11-03 | In-Progress | Planned
| 2.2 | BLUEPRINT | PROTOTYPE MODEL OF FEEDBACK FORM | VARIJA | 2024-08-03 | 2024-08-03 | 1 Day | 2024-12-03 | 2024-12-03 | In-Progress | Delay, requirement changed
| 2.3 |  | SOFTWARE TECHNICAL SPECIFICATION | VARIJA | 2024-09-03 | 2024-09-03 | 1 Day | 13/3/2024 | 13/3/2024 | In-Progress | Delay, requirement changed
| 2.4 |  | MVP-MAX VAIBLE PRODUCT | VARIJA | 2024-11-03 | 2024-11-03 | 1 Day | 13/3/2024 | 13/3/2024 | In-Progress | Delay, requirement changed
| 2.5 |  | REVIEW MEETING | NIKHIL | 2024-12-03 | 2024-12-03 | 1 Day | 14/3/2024 | 14/3/2024 | In-Progress | Delay, requirement changed
| 2.6 |  | PROJECT TIME LINE SUBMISSION | VARIJA | 13/3/2024 | 13/3/2024 | 1 Day | 15/3/2024 | 15/3/2024 | In-Progress | Delay, requirement changed
| 2.7 |  | SOFTWARE DESIGN REVIEW | MANJUNATH IYER | 13/3/2024 | 13/3/2024 | 1 Day | 16/3/2024 | 16/3/2024 | In-Progress | Delay, requirement changed
| 2.8 |  | PROJECT-CLOSURE | MANJUNATH IYER | 14/3/2024 | 14/3/2024 | 1 Day | 17/3/2024 | 17/3/2024 | In-Progress | Delay, requirement changed